## 项目规划表
The application for learning Chinese and the other languages
[5 empty] | 周期突出显示： | 1 |  |  | Plan using period |  |  |  | plan time |  |  |  |  | plan finish % |  |  |  |  | actucal working time | [5 empty] | finish(out of plan) %
Activity | Start time(week number) | Plan time(number of weeks) | Actual start time | Plan finish(number of weeks) | % finish | period
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Literature and System Survey | 1 | 5 | 1 | 4 | 100%
Model Development | 6 | 6 | 6 | 6 | 100%
Prototyping | 6 | 4 | 6 | 5 | 100%
System integration | 8 | 8 | 8 | 6 | 80%
UI development | 8 | 8 | 8 | 2 | 100%
User testing | 9 | 4 | 9 | 4 | 100%
data analysis | 13 | 3 | 13 | 2 | 100%